## Sheet1
Actions week | semester 7 | [13 empty] | semester 8
| week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14 | week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28 | week 29 | week 30
Requirement Analysis | bar: semester 7 week 1 to semester 7 week 3
Sensor Selection | bar: semester 7 week 4 to semester 7 week 6
IoT Device Selection | bar: semester 7 week 7 to semester 7 week 9
Cloud-based Database Setup | bar: semester 7 week 10 to semester 7 week 12
AI Algorithm Development | bar: semester 7 week 13 to semester 8 week 18
Alert System Development | bar: semester 8 week 19 to semester 8 week 21
Data Visualization Tool Development | bar: semester 8 week 22 to semester 8 week 26
Integration and Testing | bar: semester 8 week 27 to semester 8 week 29
Deployment | bar: semester 8 week 30
Actions | semester 7 week 1: semester 7
| week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | week 13 | week 14
Requirement Analysis | bar: semester 7 week 1 to semester 7 week 3
Sensor Selection | bar: semester 7 week 4 to semester 7 week 6
IoT Device Selection | bar: semester 7 week 7 to semester 7 week 9
Sensor design and test for selected food | bar: semester 7 week 9 to semester 7 week 14
Collect data from the developed sensor | bar: semester 7 week 13 to semester 7 week 14
Actions | semester 7 week 1: semester 8
| week 15 | week 16 | week 17 | week 18 | week 19 | week 20 | week 21 | week 22 | week 23 | week 24 | week 25 | week 26 | week 27 | week 28 | week 29 | week 30
compare the data with available data in internet | bar: semester 8 week 15 to semester 8 week 16
Develop AI Algorithm to predict food quality | bar: semester 8 week 16 to semester 8 week 21
create App to monitor the quality of food | bar: semester 8 week 18 to semester 8 week 26
develop the sensor performance and apearance | bar: semester 8 week 24 to semester 8 week 29
Finalise the project | bar: semester 8 week 29 to semester 8 week 30

## Sheet2
week 1 | project selection
week 2
week 3
week 4
week 5
week 6
week 7 | proposal evolution
week 8
week 9
week 10
week 11
week 12
week 13
week 14
week 15 | progress evolution 1
week 16
week 17
week 18
week 19
week 20
week 21
week 22 | progress evolution 2
week 23
week 24 | Report 1st submission Decide conference/journal or 2nd submission
week 25
week 26
week 27 | Report 1st submission to the coordinator
week 28 | Final oral presentation Viva voce
week 29
week 30 | Review conference paper Submission machine readable project report